Comprehensive Expert Report: Document Management and Regulatory Oversight in Nuclear Power Plant Construction

Content

Comprehensive Expert Report: Document Management and Regulatory Oversight in Nuclear Power Plant Construction 	1

I. Introduction: Documentation as a Basis for Nuclear Safety and Economics Project 	2

1.1. The Role of Documentation in the Life Cycle of a Nuclear Facility 	2

1.2. Hierarchy and Conceptual Separation of Documentation 	2

II. Classification and Hierarchy of Documentation: Comparative Analysis 	3

2.1. Design Documentation (Design / Licensing Basis) 	3

2.2. Working Documentation (Working / Detailed Engineering) 	4

2.3. As-Built Documentation and Configuration Management 	5

III. Timing, Coordination and Regulatory Oversight 	5

3.1. Regulatory Hold Points 	5

3.2. Documentation Change Management 	6

3.3. Independent Project Verification (IDVP) as a Quality Control Mechanism 	6

IV. Impact of Affiliation of the Developer of Working Documentation (DWID) 	7

4.1. Formal Regulation of OCI in the USA 	7

4.2. Consequences of Affiliation in Real Projects (Case Study) 	8

4.3. Strategies for Neutralizing OCI 	8

V. Comparative Analysis of Document Control Systems 	9

VI. Conclusion and Strategic Recommendations 	10

6.1 Key Findings of the Comparative Analysis 	10

6.2. Recommendations for Reducing Documentation Risks 	11

I. Introduction: Documentation as a Basis for Nuclear Safety and Project Economics

1.1. The Role of Documentation in the Life Cycle of a Nuclear Facility

Nuclear power plant (NPP) construction documentation represents not only a technical archive but also the formal licensing basis for the facility's operation. It is a critical tool for substantiating the safety case and ensuring the traceability of all design, construction, and operational decisions.

The International Atomic Energy Agency (IAEA) emphasizes that maintaining the physical state of a facility in accordance with its documented description (Configuration Management, CM) is fundamental to safety. Statistics show that up to 25% of reported incidents in the nuclear industry can be caused by configuration errors or deficiencies. 1 A CM system based on accurate as-built documentation ensures the timely provision of reliable information, which enables safe and cost-effective decision-making .

Historically, documentation issues in older NPP designs were primarily related to maintaining documentation up-to-date after years of operation and modifications. 2 However, modern Generation III+ NPP designs have revealed a different, more pressing problem: the insufficient maturity of the original detailed design documentation (DD) at the start of physical construction. This factor, as demonstrated by examples in the US (Vogtle) and Europe (Olkiluoto 3), has led to unprecedented delays and a multiple increase in capital costs. 3 The essence of this problem is that construction work begins before the detailed design is fully completed and verified.

1.2. Hierarchy and Conceptual Separation of Documentation

The NPP construction process involves the sequential development of three main types of documentation, each of which serves its own regulatory and technical purpose:

- Design Documentation (DD) : This level, often represented by the Safety Analysis Report (SAR), is required to obtain a Construction Permit or Combined License (COL). The DD establishes the Principal Design Criteria (PDC) 5 and demonstrates that the proposed facility protects public health and safety.6

- Working Documentation (WD) : This is a detailed DD document down to the level necessary for the immediate implementation of the project: equipment procurement, component manufacturing, installation, and testing. In the Russian context, the procedure for preparing WD for nuclear facilities (NF) is regulated by industry standards, such as STO SRO-P 60542948 00052-2017 .

- -Built Records (ABR) : Documentation that captures the actual state of a facility, i.e., the "as-built" state. It includes all modifications made during construction and serves as the basis for change management and operation of the facility throughout its life cycle. 1

Regulatory requirements, for example in the US, dictate that the Final Safety Analysis Report (FSAR) must contain sufficient design information to allow the regulator to make a final determination on all safety issues and the applicant to prepare construction specifications and acceptance requirements. 7 When the applicant fails to achieve such a high level of FSAR maturity before construction begins, the Working Documentation, which should simply be an implementation of the approved FSAR, becomes "floating" or incomplete. This creates organizational chaos, leads to the need for constant changes, and is a breeding ground for organizational conflicts of interest (OCI) and delays.

II. Classification and Hierarchy of Documentation: Comparative Analysis

2.1. Design Documentation (Design / Licensing Basis)

Regulatory approaches to Project Documentation vary across jurisdictions, but their primary purpose is to demonstrate the safety of the project.

In the United States (US), the licensing process is regulated by the Nuclear Regulatory Commission (NRC) under 10 CFR Part 50 (two-stage licensing) or 10 CFR Part 52 (combined license, COL). 6 The key document is the Safety Analysis Report (SAR) , which is first submitted as a Preliminary Report (PSAR) for a construction permit and then as a Final Report (FSAR) for an operating license. 11 The FSAR must describe and analyze the structures, systems, and components and demonstrate that safety will be ensured. It must include the General Design Criteria established in Appendix A of 10 CFR Part 50, which define the minimum requirements for systems important to safety. 5

In the Russian Federation (RF) , the primary document substantiating safety is the Safety Analysis Report (SAR) . Requirements for its content, as well as general safety principles for nuclear power plants, are established by federal rules and regulations (NRs), such as NP-001-15 ("General Provisions for Ensuring the Safety of Nuclear Power Plants") and NP-006-98 ("Requirements for the Contents of the Safety Analysis Report for Nuclear Power Plants with WWER Reactors"). 13

In European practice (EU), documentation is guided by IAEA standards, in particular, the IAEA SSR-2/1 requirements for the design of nuclear power plants 14 and the guidelines of the Western European Nuclear Regulators' Association (WENRA). 15 The purpose of the PD is to ensure a high level of safety through the implementation of the principle of in-depth protection. 16

2.2. Working Documentation (Working / Detailed Engineering)

Working Documentation (WD) translates the conceptual and licensed design (LD) into practical instructions for construction, fabrication and installation.

In the United States , the quality of Detailed Design and Construction Specifications (DDCS) must meet strict standards, the central one being ASME NQA-1: Quality Assurance Requirements for Nuclear Facility Applications . 17 In addition, the construction of nuclear components is strictly regulated by the ASME BPV Section III Code ("Rules for the Construction of Nuclear Facility Components"). 19 The American regulator incorporates these industry consensus standards into 10 CFR, which provides for enormous technical depth of quality control, extending even to such aspects as component cleaning, packaging, mechanical systems testing, and maintaining the integrity of electronic records. 18 However, this approach requires constant attention to new technologies, since advanced reactors (e.g., high-temperature reactors) may not have NRC-approved construction codes such as BPV III Division 5. 21

In the Russian Federation, the development of design documentation is regulated by national standards and SRO STOs, which establish the procedure for its preparation and execution. 8 Compliance of the design documentation with the approved design documentation and the requirements of the non-profit partnership is mandatory.

In European projects, detailed design development is often based on the EUR Document (European Utility Requirements) . This document is a continuously updated, consolidated set of European utilities' expectations for new light-water reactor (LWR) designs, including requirements for safety, performance, constructability, and economics. 22 The use of the EUR serves as a technical specification for construction applications and a guide for vendors seeking to operate in Europe. 24

2.3. As-Built Documentation and Configuration Management

As-Built documentation (AD), which records the "as-built" state, is the final, but longest-lasting type of documentation. In the United States, this is often called the "Permanent Drawing System." 9

The IAEA emphasizes that proper Configuration Management (CM) is critical to ensure that the construction, operation, maintenance and testing of a physical facility meets the design requirements expressed in the documentation. 1

One of the most vulnerable stages of a project is the transfer of the Configuration Base from the construction organization to the operator. The IAEA Safety Guide (SSG-38) requires the licensee to establish a system for the controlled transfer of work and related records (e.g., nonconformity and corrective action reports) between different groups, which is necessary to demonstrate compliance with regulations. 25 The transition from traditional paper-based documentation systems to modern data-centric technologies using IT tools is recognized as an important step in increasing data reliability and improving CM. 2

III. Timing, Coordination and Regulatory Oversight

Timely submission of documentation is key to maintaining construction schedules. Regulators use various mechanisms to monitor this process, but their effectiveness often depends on the project's organizational maturity.

3.1. Regulatory Hold Points

A common principle of international regulation is the use of "hold points"—points when physical construction or production of critical components cannot proceed without formal approval from the regulatory body. 25 These hold points concern the approval of detailed designs, manufacturing documentation, and inspection results. 26

However, experience with new-generation nuclear power plant construction has shown that formal stoppages do not guarantee success if the project's organizational structure encourages bypassing them. In the case of Olkiluoto 3 (OL3) in Finland, the regulator STUK discovered that design documentation was being developed and evaluated in parallel with , or even after , the actual equipment manufacture. 27 This pressure on a fast-track approach, arising under a turnkey contract, led to the need to introduce changes during manufacture and installation. The regulator was forced to strengthen "close monitoring and supervision" 28 to ensure quality, which, in essence, was a reaction to inadequate oversight by the licensee itself.

3.2. Documentation Change Management

On large projects where the design was not fully completed before construction began (e.g. Vogtle 3 and 4), change management became a source of significant delays.

In the United States, as part of the combined licensing (COL) process, the NRC uses mechanisms to process Requests for Additional Information (RAIs) and Notices of Change (UINs/ICNs). 29 An excessive number of such requests and notices is a clear indication of the immaturity of the original Design Documentation. To manage this volume of changes, the NRC created a specialized organizational structure (Division of Construction Inspection Programs, DCIP, which became VPO) to review UINs and ICNs. 29

The problem here is this: when the number of changes becomes critically large, it not only slows down the project but also shifts the regulator's role. The regulator is forced to spend resources reviewing basic engineering decisions, essentially participating in design refinements , instead of simply verifying its compliance with the approved baseline. 4 This significantly increases regulatory timelines and is the main factor explaining why projects like Vogtle have faced decade-long delays.

3.3. Independent Project Verification (IDVP) as a Quality Control Mechanism

The Independent Design Verification Program (IDVP) is used in the United States as an important mechanism for mitigating risks associated with documentation quality and conflicts of interest. IDVP is a critical preventative measure aimed at ensuring that the detailed design complies with FSARs, NRC regulations, and other applicant obligations. 30

The IDVP process involves engaging an external, impartial team, often consisting of contractor specialists in mechanical, electrical, and instrumentation systems, to review key documents, including the FSAR and Probabilistic Risk Analysis (PRA). This team evaluates the completeness and adequacy of the applicant's own design review. 30

The use of IDVP or similar external review procedures for Working Documentation is an effective way to neutralise the internal pressure of the OCI, as it provides an objective assessment of the design basis before its deficiencies are "sealed" into the design.

IV. Impact of Affiliation of the Working Documentation Developer (WDD)

The issue of organizational affiliation of the developer of the Working Documentation, especially when he is affiliated with the general contractor or manufacturer, represents a key risk to the safety and economics of the project, known as Organizational Conflict of Interest (OCI).

4.1. Formal Regulation of OCI in the USA

In the United States, OCI issues are formally regulated by the Federal Acquisition Regulations (FAR Subpart 9.5) and the NRC procurement regulations (NRCAR Subpart 2009.5). 31 Although these regulations primarily apply to contractors working directly for the government (NRC, DOE, NNSA), their philosophy is aimed at preventing situations in which the contractor's interests could create bias or undermine objectivity. 33

OCI is considered most likely in contracts involving management support, consulting services, or, most importantly, when the contractor performs systems engineering and technical management work, unless the contractor has overall contractual responsibility for the final product. 31 The goal is to ensure that services are provided without financial or organizational bias.

4.2. Consequences of Affiliation in Real Projects (Case Study)

Organizational affiliation, when the developer of the design documentation is located in the same corporate structure as the builder or vendor (EPC or turnkey model), creates an internal incentive to speed up construction and ignore the incompleteness of the design.

- Vogtle 3 and 4 Project (USA) : This project, using the AP1000 design, suffered delays that doubled the cost to over $30 billion. 3 A key reason for the organizational failure was incomplete engineering design finalization . 4 The vendor-controlled design and construction model allowed physical work to begin despite the lack of mature working documentation. As a result, construction was forced to work from constantly changing drawings, leading to massive rework and regulatory overload.

- Olkiluoto 3 Project (Finland/EU) : The turnkey project 26 experienced significant problems related to the quality and timeliness of the design documentation. An STUK investigation found that organizational and programmatic deficiencies, as well as inadequate on-site inspections, led to errors such as the mixing up of hundreds of internal valve parts during installation. 34 However, the complexity of the project, involving an extensive multinational network of subcontractors 35 and the fact that the documentation was prepared in parallel with production, meant that traditional supervision methods were ineffective. 27 This demonstrates that in the presence of a QCI (in this case, where the contractor controls both design and production), traditional quality control mechanisms and procedural oversight are insufficient.

4.3. Strategies for Neutralizing OCI

Effective management of a nuclear power plant project requires organizational measures aimed at countering internal pressures caused by affiliation:

- Organizational Separation of Design Authority: The Licensee (Owner/Operator) must ensure that the Design Authority function (the unit responsible for project safety) is formally and effectively separated from Construction Management. 25

- Contractual Conditions: EPC (engineering, procurement, construction) contracts must include strong financial incentives and design completion milestones , not just physical construction work.

- Independent Verification (IDVP): The establishment of an independent external verification mechanism for Work Documentation prior to critical manufacturing or installation stages, such as the NRC 30 IDVP , is the most powerful institutional tool for neutralizing internal QCI.

V. Comparative Analysis of Document Control Systems

Documentation control systems in the nuclear sector are based on common international principles (IAEA), but have significant differences in implementation, particularly with regard to the level of detail of technical standards and regulatory oversight methods.

The summary table presents key aspects of document management in the three compared jurisdictions:

| Criterion | Russian Federation (RF) | United States (USA) | European Practice (EU/WENRA) |
| --- | --- | --- | --- |
| Regulatory Authority | Rostekhnadzor (licensing, design review) | NRC (10 CFR Part 50/52) | National authorities (STUK, ASN); ENSREG |
| Key QA Standard | NP-011, GOST, STO SRO 8 | ASME NQA-1 (mandatory) 17 | IAEA GS-R-3; WENRA SRLs (Issue C: Management System) 36 |
| Philosophy of Supervision | Strict state supervision and examination of design documentation. | Direct regulation (10 CFR); ASME (Advanced Mechanical Engineering Standards Corporation). | Harmonization (WENRA, EUR); Strict national supervision (Hold Points). |
| Regulation of Deadlines | Determined by the project phases and NP requirements. | Strictly linked to licensing stages (PSAR/FSAR). 6 | Determined by the national regulator; Significant delays in the implementation of new projects. 26 |

The United States demonstrates the most formalized approach to technical quality assurance (QA) through the mandatory application of NQA-1, which covers in detail all aspects of document management, from component cleaning to maintaining electronic records. 18 Furthermore, the US legal system explicitly regulates organizational conflicts of interest (OCI) issues for contractors. 31

Despite national fragmentation, European practice utilizes the EUR Document —a unique set of requirements based on half a century of LWR operating experience. 22 This document allows for the early establishment of clear technical expectations for safety and design, which is a powerful preventative measure that creates a unified technical basis for RD developers. However, as OL3's experience has shown, even with clear requirements, insufficient oversight by the licensee and organizational problems in the subcontractor chain can lead to schedule delays and documentation issues. 34

Ultimately, regardless of jurisdiction, the success of a project is determined not only by the strictness of regulations (NP or 10 CFR), but also by the organizational maturity of the licensee, which is able to ensure the independence of engineering from construction pressures.

VI. Conclusion and Strategic Recommendations

6.1 Key Findings of the Comparative Analysis

Analysis shows that documentation is a key asset, and its quality and timeliness directly impact the cost and timeframe of nuclear power plant construction. The main problem identified in modern Generation III+ nuclear projects worldwide is the insufficient maturity of the Design and Working Documentation at the start of physical construction.

The organizational affiliation of the developer of working documentation with the builder (OKI) is a key catalyst for this problem. In EPC or turnkey construction schemes, the general contractor's financial incentives often prioritize construction speed over engineering quality, leading to the preparation of working documentation in parallel with or after fabrication, as observed in Olkiluoto 3 and Vogtle. This results in regulatory overload (in the form of massive change management) and the emergence of critical discrepancies between the design and the actual construction.

6.2. Recommendations for Reducing Documentation Risks

To ensure the safety, timeliness, and cost predictability of nuclear construction, it is necessary to implement organizational and technical strategies aimed at early engineering maturity and the neutralization of critical infrastructure issues:

- Ensuring RD Maturity: The Licensee must establish and strictly adhere to the requirement for achieving a minimum of 90% completeness of the Working Documentation for critical systems prior to mass production or installation. This reduces the need for constant changes that overload the regulator and the construction site.

- Institutionalization of Independent Verification (IDVP): Implementation of a mechanism for independent, external verification of working documentation before critical construction stages. Following the example of NRC IDVP 30 , this practice should become standard for large nuclear projects in EPC models, ensuring an impartial assessment of the working documentation's compliance with the licensing basis.

- Separation of Responsibility: Ensuring an organizational hierarchy in which Design Authority is formally and functionally separated from Construction Management . The IAEA requires that the operating organization have a formally designated unit responsible for design safety to ensure continued safety. 25

- Transition to Data-Centric Management: Using modern information systems for configuration management. Transitioning from paper-based to data-centric documentation improves data reliability, facilitates change management, and prevents configuration errors throughout the life of the NPP.

| Type of Risk (Consequence of OKI) | Mechanism of Origin | Example of Risk Realization | Risk Mitigation Strategy |
| --- | --- | --- | --- |
| Late Design Changes | Pressure to accelerate construction with incomplete working documentation; Hidden acceptance of defects. | Vogtle 3&4: Incomplete Engineering (UIN/ICN). 4 | Mandatory IDVP; Regulatory breakpoints tied to design maturity. |
| As-Built Records Inconsistency | An affiliated developer of design documentation fails to promptly update drawings or approves deviations without adequate analysis. | Olkiluoto 3: Parallel preparation of RD and production; Installation errors. 27 | Formal organizational separation of Design Authority and Construction Management; Strict Configuration Management (CM). |
| Distortion of QA Reporting | An affiliated contractor understates the number of nonconformities to meet contract deadlines. | General risk addressed by NQA-1 records requirements. 18 | Mandatory audit of the Quality Management System by independent external bodies. |

To successfully construct a nuclear power plant on time and within budget, the project's organizational structure must be designed to eliminate conflicts of interest that would motivate the developer of the detailed design documentation to prioritize the speed of completion over the quality of engineering solutions. This is a requirement for the highest organizational maturity on the part of the Licensee.

Sources

- Configuration management in nuclear power plants, accessed October 18, 2025, https://www-pub.iaea.org/MTCD/Publications/PDF/te_1335_web.pdf

- Information technology impact on nuclear power plant documentation, accessed October 18, 2025, https://www-pub.iaea.org/MTCD/Publications/PDF/te_1284_prn.pdf

- Plant Vogtle Unit 4 begins commercial operation - US Energy Information Administration (EIA), last accessed: October 18, 2025, https://www.eia.gov/todayinenergy/detail.php?id=61963

- Mixed Milestone: What Vogtle Can Teach Us About the Future of US Nuclear Energy, accessed October 18, 2025, https://www.catf.us/2023/09/mixed-milestone-vogtle-teach-about-future-us-nuclear-energy/

- Appendix A to Part 50—General Design Criteria for Nuclear Power Plants - NRC, last accessed October 18, 2025, https://www.nrc.gov/reading-rm/doc-collections/cfr/part050/part050-appa

- Nuclear Power Plant Licensing Process, accessed October 18, 2025, https://wyoleg.gov/InterimCommittee/2023/09-2023071715-03NuclearPowerPlantLicensingProcess.pdf

- § 52.157 Contents of applications; technical information in the final safety analysis report. | Nuclear Regulatory Commission, last accessed October 18, 2025, https://www.nrc.gov/reading-rm/doc-collections/cfr/part052/part052-0157

- Download STO SRO-P 60542948 00052-2017 Standard ..., last accessed: October 18, 2025, https://meganorm.ru/Index2/1/4293727/4293727331.htm

- Plant Procedure 7.2.6, "Engineering Change Process," Revision 1. - NRC, last accessed: October 18, 2025, https://www.nrc.gov/docs/ML0307/ML030710641.pdf

- NUREG/BR-0298 Rev 2 "Nuclear Power Plant Licensing Process," accessed October 18, 2025, https://www.nrc.gov/docs/ml0421/ml042120007.pdf

- Standard Format and Content of Safety Analysis Reports for Nuclear Power Plants, Revision 0, accessed October 18, 2025, https://www.nrc.gov/docs/ML1125/ML11255A151.pdf

- FINAL SAFETY ANALYSIS REPORT VOLUME 1 - INL Digital Library, accessed October 18, 2025, https://inldigitallibrary.inl.gov/PRR/71538.pdf

- List of regulatory documents used by the Certification Body for certification of products in the field of atomic energy use - ANO AtomTechnoTest, last accessed: October 18, 2025, http://atomtechnotest.ru/applicant/OIAE/std/

- Safety of Nuclear Power Plants: Design | IAEA, accessed October 18, 2025, https://www.iaea.org/publications/10885/safety-of-nuclear-power-plants-design

- WENRA Reactor Safety Reference Levels January 2008 - ASN, accessed October 18, 2025, https://reglementation-controle.asnr.fr/content/download/85915/file/WENRA%20Reactor%20Safety%20Reference%20Levels%20for%20NPP%20-%20January%202008.pdf

- Design of Nuclear Power Plants | IAEA, accessed October 18, 2025, https://www.iaea.org/topics/design

- Nuclear Quality Assurance (NQA-1) Certification - ASME, accessed October 18, 2025, https://www.asme.org/certification-accreditation/nuclear-quality-assurance-nqa1-certification

- ASME NQA-1-2024: Nuclear Facility Applications - The ANSI Blog, accessed October 18, 2025, https://blog.ansi.org/ansi/asme-nqa-1-2024-nuclear-facility-applications/

- RESOURCES FOR THE NUCLEAR INDUSTRY - ASME, accessed October 18, 2025, https://www.asme.org/wwwasmeorg/media/resourcefiles/shop/standards/new%20releases/nuclear-resources-brochure.pdf

- ASME Advanced Reactor Standards Development NRC, DOE, and National Laboratory Support, accessed October 18, 2025, https://www.nrc.gov/docs/ML2409/ML24094A008.pdf

- NUREG-2245, "Technical Review of the 2017 Edition of ASME Code, Section III, Division 5, "High Temperature Reactors" - NRC, last accessed October 18, 2025, https://www.nrc.gov/docs/ML2303/ML23030B636.pdf

- The EUR Document, accessed October 18, 2025, https://europeanutilityrequirements.eu/sites/default/files/Resources/EUR%20Document.pdf

- European Utility Requirements for LWR Nuclear Power Plants, accessed October 18, 2025, https://na.eventscloud.com/file_uploads/232a4dcc136b711ec07c48725bbc421c_CORDEL4RWSEURleaflet2019.pdf

- European Utility Requirements for LWR Nuclear Power Plants - Scientific, Technical Publications in the Nuclear Field | IAEA, accessed October 18, 2025, https://www-pub.iaea.org/MTCD/publications/PDF/P1500_CD_Web/htm/pdf/topic3/3S01_P.%20Berbey_PM.pdf

- Construction for nuclear installations - Scientific, technical ..., accessed October 18, 2025, https://www-pub.iaea.org/MTCD/publications/PDF/Pub1693Web-54107132.pdf

- if lkil Experience from Olkiluoto 3 EPR - ENSREG |, accessed October 18, 2025, https://www.ensreg.eu/sites/default/files/conference/29%2006%202011/SESSION%202/PART%201/Petteri%20Tiippana%20Olkiluoto%203%20experience%20for%20ENSREG%20conference.pdf

- Investigation of the procurement and supply of emergency diesel generators (EDG) and related auxiliary systems - STUK, accessed October 18, 2025, https://stuk.fi/documents/150192312/0/OL3-EDG-investigation-report.pdf/2c22d173-7a55-c863-2b99-2ffedde941bd/OL3-EDG-investigation-report.pdf?t=1717669372037

- Lessons Learned from Olkiluoto 3 Plant - Power Engineering, accessed October 18, 2025, https://www.power-eng.com/nuclear/lessons-learned-from-olkiluoto-3-plant/

- Vogtle, Units 3 and 4, and VC Summer, Units 2 and 3, 10 CFR Part 52 Construction Lessons-Learned Report - NRC, accessed October 18, 2025, https://www.nrc.gov/docs/ML2332/ML23325A202.pdf

- IP 93814, "Independent Design Verification Program." - NRC, last accessed: October 18, 2025, https://www.nrc.gov/docs/ML1027/ML102780207.pdf

- Subpart 9.5 - Organizational and Consultant Conflicts of Interest | Acquisition.GOV, last accessed October 18, 2025, https://www.acquisition.gov/far/subpart-9.5

- Subpart 2009.5 - Organizational Conflicts of Interest | Acquisition.GOV, accessed October 18, 2025, https://www.acquisition.gov/nrcar/subpart-2009.5-organizational-conflicts-interest

- NNSA Supplement to the DOE Acquisition Guide: Pre- and Post-Award Guidance for Identifying and Documenting Contractors, accessed October 18, 2025, https://www.energy.gov/management/articles/nnsa-supplement

- Third Construction Experience Synthesis Report - OECD, accessed October 18, 2025, https://one.oecd.org/document/NEA/CNRA/R(2021)1/en/pdf

- Managing Safety in Subcontractor Networks: The Case of Olkiluoto3 Nuclear Power Plant Construction Project - Presses des Mines - Open edition books, accessed October 18, 2025, https://books.openedition.org/pressesmines/1065?lang=en

- Report WENRA Safety Reference Levels for Existing Research Reactors -, last accessed: October 18, 2025, https://www.wenra.eu/sites/default/files/publications/wenra_safety_reference_levels_for_research_reactors__final__november_2020.pdf

- Report WENRA Safety Reference Levels for Existing Reactors 2020 -, last accessed: October 18, 2025, https://www.wenra.eu/sites/default/files/publications/wenra_safety_reference_level_for_existing_reactors_2020.pdf